## Overview
AI-Company Master Plan | Phase 2 — Real Data Integration
Version | 1.0
Status | In Progress
Owner | CEO / PMO
Last Updated | 2026-06-03

## Milestones
ID | Milestone | Target | Status | Owner
M1 | PMO foundation | Week 1 | Complete | PMO
M2 | Phase 2 integration plan | Week 1 | Complete | Engineering
M3 | GitHub connector v1 | Week 2 | In Progress | Engineering
M4 | Supabase connector v1 | Week 2 | In Progress | Engineering
M5 | Health score service | Week 2 | Planned | Engineering
M6 | Production metrics dashboard | Week 3 | Planned | Engineering
M7 | Daily CEO brief generator | Week 3 | Planned | Chief of Staff
M8 | Phase 2 validation | Week 4 | Planned | PMO

## Workstreams
Workstream | Lead | Deliverables | Dependencies
Data connectors | Engineering | GitHub + Supabase v1 | Credentials
Health & metrics | Engineering | Deterministic health score | Connectors
CEO dashboard | Engineering | Production metrics UI | Health + connectors
Executive AI | Chief of Staff | Daily brief (explain only) | Metrics

## Resources
Role | Allocation % | Notes
Lead Engineer | 60 | Phase 2 execution
CEO | 10 | Approvals + validation
PMO | 15 | Status + risk tracking
AI executives | 0 | Frozen — no new roles